## Sheet1
NLP Project Preference Document |  |  |  | IT9002
Mentor : Sini Raj Pulari
Project Name: | Amazon Product Reviews Sentiment Analysis
Student Name: | JAAFAR ISA MOHAMED AHMED |  |  | Student I ID:
NLP Project Log File |  |  |  | 202508989
Date | Week No | Task Name | Work done During the week | Issues Experienced if any
(Bullet points /Description)
2025-10-23 | 1 | Problem Selection and Literature Review | Chosen project topic | None
Read about sentiment analysis
Defined project goal
2025-10-30 | 2 | Dataset Collection and Understanding | Downloaded dataset | None
Checked labels and size
Displayed sample data
2025-11-06 | 3 | Text Preprocessing Implementation | Cleaned text | None
Tokenized sentences
Removed stopwords
Applied lemmatization
2025-11-13 | 4 | Text Representation Techniques | Created TF-IDF features | None
Visualized frequent words
2025-11-20 | 5 | Model Implementation | Trained Logistic Regression | None
Compared accuracy
2025-11-27 | 6 | Model Evaluation and Visualization | Calculated metrics | None
Created confusion matrix
Compared model results
2025-12-04 | 7 | Report Writing and Documentation | Wrote report sections | None
Added figures and tables
Last changes
2026-01-08 | 8 | Project Submition